## Sheet1
Task Name | Start Date | End Date | Dependency
Planning | 03/01/2020 | 03/01/2020
Conduct kickoff meeting | 03/01/2020 | 03/01/2020
Concept exploration | 03/01/2020 | 03/01/2020 | Conduct kickoff meeting
Project scheduling | 03/01/2020 | 03/01/2020 | Conduct kickoff meeting
Plan organize | 03/01/2020 | 03/01/2020 | Conduct kickoff meeting
Define SW running environment | 03/01/2020 | 03/01/2020 | Conduct kickoff meeting
Requirements Analysis | 03/02/2020 | 03/03/2020
Review assignment outline | 03/02/2020 | 03/02/2020
User meeting | 03/03/2020 | 03/03/2020 | Review assignment outline
Analyze functions | 03/02/2020 | 03/02/2020 | Review assignment outline
Define and develop preliminary SW requirements | 03/02/2020 | 03/02/2020 | Analyze functions
Define scope statement | 03/02/2020 | 03/02/2020 | Review assignment outline
Design | 03/04/2020 | 03/06/2020
Process status meeting | 03/04/2020 | 03/04/2020 | Requirements Analysis
Identify scenario | 03/04/2020 | 03/04/2020 | Process status meeting
Choose a language for coding | 03/04/2020 | 03/04/2020 | Process status meeting
Database design | 03/04/2020 | 03/05/2020 | Process status meeting
Algorithm design | 03/04/2020 | 03/05/2020 | Process status meeting
Interfaces design | 03/04/2020 | 03/05/2020 | Process status meeting
Software prototyping | 03/05/2020 | 03/06/2020 | Interfaces design
Development and Coding | 03/06/2020 | 03/09/2020
Develop a database | 03/06/2020 | 03/07/2020 | Design
Develop algorithms | 03/07/2020 | 03/07/2020 | Develop a database
Develop a user interface | 03/07/2020 | 03/09/2020 | Develop algorithms
Debugging | 03/09/2020 | 03/09/2020 | Develop a user interface
Testing | 03/09/2020 | 03/10/2020
Install the SW | 03/09/2020 | 03/09/2020 | Development and Coding
Create test code | 03/09/2020 | 03/09/2020 | Development and Coding
Software testing | 03/10/2020 | 03/10/2020 | Create test code
Integration testing | 03/10/2020 | 03/10/2020 | Development and Coding
Performance testing | 03/10/2020 | 03/10/2020 | Development and Coding
Deployment | 03/10/2020 | 03/10/2020
Deployed SW | 03/10/2020 | 03/10/2020 | Testing
Upload SW to repository | 03/10/2020 | 03/10/2020 | Deployed SW
Create README file | 03/10/2020 | 03/10/2020 | Deployed SW
Retrieve outputs | 03/10/2020 | 03/10/2020 | Deployed SW